## Backlog
Epic | User Story | Acceptance Criteria | Notes / Technical Considerations
MVP3 IA + Routes | As a user, I want a coherent primary navigation so I can move between execution surfaces without dead ends. | ☐ Primary nav matches agreed MVP3 set (Today, Relationships, Lists, Workflows, Settings; Insights per roadmap) ☐ Legacy URLs redirect correctly ☐ Activity / materials / search access matches product decision (in nav vs linked) | IN REPO: Six-item rail + bottom nav in app-shell.tsx. GAP (MVP3): Activity not in primary nav; header search and global fund selector still product gaps per MVP doc §3.
Tomo Orchestration | As a user, I want Tomo to act with the right tools on each surface so assistance is safe and relevant. | ☐ Tool allow-lists match surface (e.g. workflow vs drawer vs general) ☐ CRM/workflow updates persist with audit for material actions ☐ filter_relationships / NL filters stay in sync with Relationships UI | IN REPO: src/app/api/tomo/orchestrate/route.ts; tools include filter_relationships, update_workflow, update_crm, draft_reply, create_user_workflow (where enabled). GAP: Persistence and RBAC per MVP doc §3.3. See MVP Appendix B and docs/WORKFLOW_CREATOR_ORCHESTRATOR_PLAN.md.
Trust + Demo Polish (Phase 0–1) | As a GP, I want consistent terminology and reliable Today/Relationships behavior so demos are credible. | ☐ Relationships filter vs action chips behave correctly (no full chip reset) ☐ Attribution uses agreed standard (GP / TOMO, not generic "User") ☐ Signal (not legacy "Momentum") naming + evidence copy ☐ Incomplete Today cards carry forward (no bogus midnight reset) | Tracked in: PRODUCT_DECISIONS_V1_PHASED_IMPLEMENTATION_PLAN.md Phase 0–1. Coordinate with pipeline Lists labeling in nav (Lists at /pipeline).
Workspace + Identity Model | As a company admin, I want to create and manage a workspace so my team can collaborate in one CRM environment. | ☐ Admin can create workspace and invite users by email ☐ User can accept invite and join correct workspace ☐ Users cannot access records outside their workspace | Add core tables: workspaces, workspace_memberships, roles; enforce workspace_id on all shared CRM entities; support invite lifecycle (pending, accepted, expired, revoked). MOCK TODAY: No durable multi-tenant backend.
Authentication + Session Security | As a user, I want secure sign-in so my account and data are protected. | ☐ Support Google and Microsoft login (plus email/password optional) ☐ Sessions expire and refresh safely ☐ Sign-out revokes access immediately | IN REPO: /auth UI with OAuth buttons and plan selection; session via src/lib/auth.ts patterns. GAP: Move to server-validated tokens; no secrets in browser for production.
Roles + Permissions (RBAC) | As an admin, I want role-based controls so users have appropriate access. | ☐ Admin / Partner / Analyst roles enforced for Team workspaces ☐ user-class role can use CRM but cannot manage admin-only areas ☐ Dedicated it_ops_support role can access user-private data only under strict controls | MVP3 ship intent names roles: Admin, Partner, Analyst (see Tomo MVP §3.4). IN REPO: Plan choice UI; no enforced server RBAC. Enforce at API; permission matrix; audit role changes.
Shared CRM + Personal Contacts | As a user, I want personal contacts visible only to me while still accessing shared company CRM. | ☐ Shared contacts visible to all workspace members per role rules ☐ Personal contacts, mail, and calendar never visible to company admins ☐ Only owner (and approved it_ops_support) can access personal data ☐ User can promote a personal contact into shared CRM with explicit action | Ownership model (scope: workspace¦personal, owner_user_id); harden search/filter/export; merge flows for duplicates. Not fully implemented in mock data layer.
Onboarding + Workspace Setup | As a new user, I want guided onboarding so I can connect tools and start quickly. | ☐ Onboarding persists progress across sessions ☐ User can skip optional steps and finish setup ☐ Connected statuses appear in settings and onboarding completion state | IN REPO: Eight-step flow src/app/onboarding/page.tsx (totalSteps = 8). GAP: Persist server-side; CSV-first import + mapping + dedupe per MVP doc Appendix C.2.
Google Integration Suite | As a user, I want Gmail, Google Calendar, and Google Contacts integrated so TOMO can assist with daily workflow. | ☐ User can connect Google account once and grant required scopes ☐ Calendar/events and contacts sync run successfully with visible status ☐ MVP is read-only sync (no write-back to Google) ☐ User can use Tomo chat to push relevant personal-contact updates into shared CRM | IN REPO: Stub connect flows. Production: OAuth, server token storage, webhooks/polling, least-privilege scopes.
Microsoft Integration Suite | As a user, I want Outlook Mail, Calendar, and Contacts integrated so TOMO works with Microsoft 365. | ☐ User can connect Microsoft account and grant Graph scopes ☐ Mail/calendar/contacts sync works with clear status/errors ☐ MVP is read-only sync (no write-back to Microsoft) ☐ Reconnect flow handles expired/revoked consent | Mirror Google via Microsoft Graph; provider abstraction; tenant admin consent for enterprises. Stubs in UI today.
Slack Integration | As a user, I want Slack connection so I can receive recaps and interact with TOMO in workspace tools. | ☐ Admin/user can install app to Slack workspace with OAuth ☐ Recaps and notifications delivered to expected channel/DM ☐ Incoming Slack actions/commands are authenticated and processed | MVP3: Narrow Slack V1 (e.g. daily brief scope), not a full messaging OS — see MVP doc §3–4. Product plan: test/send + webhook flows in later phases (PRODUCT_DECISIONS Phase 2).
Affinity Integration | As an operations user, I want to sync Affinity people/companies so TOMO starts with existing CRM data. | ☐ Workspace admin sees guided setup steps requiring Affinity admin API key + List ID ☐ App validates credentials immediately (test call) before marking connected ☐ Initial import and incremental sync run with dedupe and mapping rules ☐ Sync failures logged with actionable retry states | Checklist UI + secure secret handling (encrypt, mask, rotate). IN REPO: Settings/onboarding placeholders only until backend exists. See Affinity setup section in backlog doc.
Google Sheets Integration | As a user, I want to export/sync CRM to Google Sheets for flexible reporting. | ☐ User can authenticate and create/select sheet destination ☐ Export produces correct schema and row counts ☐ Sync mode (export-only or bidirectional) is clearly defined | Track external_sheet_id, job history, schema drift from manual edits.
Billing + Subscription (Stripe) | As an admin, I want to manage plan, seats, and payment so workspace billing is reliable. | ☐ Workspace-level billing supported in v1 (single payer per workspace) ☐ Team plans support seat management and proration ☐ Webhooks keep subscription status accurate in app | IN REPO: Stripe placeholders in settings. GAP: Checkout, Portal, webhooks, stripe_customer_id on workspace, entitlement gating.
Settings + Preferences | As a user, I want profile, notification, and integration settings so I can control my experience. | ☐ User can update profile and notification routing per channel ☐ Admin can manage workspace-wide settings separately from personal settings ☐ Settings changes persist and are audited for critical fields | IN REPO: src/app/settings/page.tsx — profile, funds, integrations, notifications, billing; five-section / connection-health evolution per PRODUCT_DECISIONS Phase 2.
Activity, Materials + Insights | As a user, I want traceability and optional analytics so I can see what changed and how we are trending. | ☐ Activity feed matches material CRM and Tomo events with filters/export where promised ☐ Insights, if in nav, is clearly 'beta' or production per roadmap ☐ Materials/briefs behavior matches IA (e.g. /materials?tab=briefs) | IN REPO: Activity at /activity (filterable mock); Insights demo at /insights (Singapore-style mock metrics) — not all locked as MVP3 core per MVP doc §2–3. Materials prototype at /materials.
Audit, Compliance + Enterprise Security | As an enterprise buyer, I want controls and logs so adoption meets security/compliance standards. | ☐ Critical actions (role change, export, integration connect/disconnect, billing changes) are audited ☐ Data export and deletion workflows are available ☐ Access controls are testable and documented | Add audit_logs (actor, action, target, time, metadata); GDPR/CCPA; retention; evidence for SOC2.
Reliability + Operations | As an internal operator, I want observability and safe background jobs so integrations stay healthy. | ☐ Sync jobs are queued, retryable, and idempotent ☐ Failures surface in dashboard/alerts ☐ APIs expose health and rate-limit protections | Queue + DLQ; logs/metrics/traces; SLOs for sync/API; circuit breakers. Partial: e.g. GET /api/version for build id.

## Enterprise Items & Gaps
Item / Area | Detail
Additional Enterprise Items (likely missing from MVP3 backlog)
SSO + Enterprise Provisioning (v2) | SAML/OIDC SSO, SCIM user provisioning/deprovisioning. Not in v1 baseline per MVP doc.
MFA + Conditional Access | Required MFA policies, device/location risk controls.
Granular Data Access Model | Field-level restrictions and export controls for sensitive data.
Approval Workflows | Admin approval for high-risk automations and bulk updates.
Data Governance | Retention windows, legal hold, backup/restore, disaster recovery targets.
Observability + Support Tooling | Admin diagnostics, sync job monitor, customer support impersonation with strict audit.
Contract / Billing Ops | Invoices, tax handling, failed payment grace periods, dunning.
Performance + Scale | Pagination/indexing for large CRM datasets and search relevance tuning.
Affinity Setup — Easy + Secure (Recommended Flow)
Step 1 — Wizard | Workspace admin clicks Connect Affinity and sees a short wizard with: what is needed (Affinity List ID + Affinity API key), who must do it (customer Affinity admin), and copyable short instructions.
Step 2 — Validation | Admin pastes key once; backend performs immediate validation call before proceeding.
Step 3 — Secure storage | On success, store encrypted secret server-side, show only masked fingerprint (••••1234), and set health status.
Step 4 — Key management | Provide Rotate key and Disconnect actions; both audited.
Step 5 — Error handling | If validation fails, show actionable error (invalid key / insufficient permissions / wrong list id) without exposing sensitive values.

## Phasing & Decisions
# | Area / Item | Detail
Recommended Implementation Order
1 | Phase 0 — Stabilisation | Chip behavior, attribution, Signal naming, Today carry-forward, verification gates — per docs/PRODUCT_DECISIONS_V1_PHASED_IMPLEMENTATION_PLAN.md.
2 | Phase 1 — Safety + Demo-critical | Workflow guardrails (dedupe, overlap, suppression), Today drawer/append behavior, required workflow diagram labels, Lists naming alignment.
3 | Durable Model | Workspace, membership, server auth, tenant-scoped APIs.
4 | OAuth + Token Lifecycle | Google and Microsoft OAuth (read paths first).
5 | Shared vs Personal Data | Data model and UI enforcement for shared vs personal contacts/integrations.
6 | Stripe Billing + Entitlements | Live billing, Checkout, Customer Portal, entitlement gating.
7 | Audit + Job Orchestration | Audit log + job orchestration for integration sync.
Confirmed v1 / MVP3 Decisions (confirm in Tomo MVP doc)
1 | Private contacts | Company admins CANNOT access user-private contacts, mail, or calendar.
2 | it_ops_support | Internal it_ops_support can access private data only under SOC2-style controls and full audit.
3 | Read-only integrations | Personal Google/Microsoft integrations are read-only in MVP (no write-back) unless product revises.
4 | Human-in-the-loop CRM | Users can use Tomo to move relevant personal-contact updates into company CRM (HITL).
5 | Source of truth | Company CRM is source of truth for shared contacts/relationships.
6 | No SSO/SCIM in v1 | No SSO/SCIM in v1 baseline — plan for v2 per MVP doc.
7 | Workspace-level billing | Billing workspace-level in v1; fund/sub-team billing later.
8 | Messaging scope | Telegram / broad messaging OS-style Slack OUT of MVP3 baseline. Slack V1 scoped (e.g. daily brief) per MVP doc.

## Context & Stack
Area | Detail
Document purpose | Epic → User story → Acceptance criteria → Engineering notes. Authoritative product + mock inventory: docs/Tomo MVP (April 24, 2026).md Delivery phasing: docs/PRODUCT_DECISIONS_V1_PHASED_IMPLEMENTATION_PLAN.md
Practical rules | Epic = big area User story = user need Acceptance criteria = business / test detail Notes / technical considerations = implementation guidance (point to routes, APIs, and known stubs)
Stack | Next.js 16 (App Router), React 19, Tailwind 4, Vercel AI SDK, Zod 4, Sonner
Primary shell nav | src/components/app-shell.tsx: Today → /home Relationships → /relationships Lists → /pipeline Workflows → /workflows Insights → /insights (secondary) Settings → /settings (secondary) Desktop rail + mobile bottom bar use the same six items.
Implemented (not main rail) | Activity (/activity), Materials (/materials), LP Network (/lp-network, /lp-network/mandate — fund selector in header on LP Network only), standalone /search
Legacy redirects | /targets → /pipeline /today → /home /tasks → /home (client redirect) /contacts → /relationships /workflow → /workflows /briefs → /materials?tab=briefs
Tomo AI endpoint | POST /api/tomo/orchestrate (streaming; tools and context.surface vary) Related: POST /api/tomo/filter-relationships, GET /api/version Demo/cron: src/app/api/cron/ and src/app/api/email/daily-brief/ Today uses inline chat wired to same orchestrator with optional todayContext (actions, commitments, daily brief blocks). Shell Tomo (FAB → dock/sheet on many routes) calls /api/tomo/orchestrate with surface: "general". Many tool apply paths are still stub / partial vs a production DB.
Auth / session | Mock session + onboarding flags (e.g. src/lib/auth.ts, local persistence) — NOT production OAuth or tenant isolation.
Integrations / billing | Settings and onboarding show Google, Microsoft, Affinity, Sheets, Slack, Stripe, etc.; most flows are UI and local flags, not live OAuth or webhooks.
Last updated | April 24, 2026 — aligned to tomo_crm (MVP3 prototype)