## Feature Tracker
TOMO — Feature Tracker: MVP3 vs Built vs Roadmap
Source: Meeting notes Feb–Apr 2026, Tomo_MVP_3_amended_v5.docx, local codebase (tomo_crm). Last updated: April 2026.
Feature / Idea | Category | Source | MVP3 Doc | Code Status | Notes / Details | Roadmap Tier
TODAY / HOME
On My Radar (renamed from Daily Brief button) | Today / Home | Ken x G (15 Apr), Geoff/Ken (16 Apr) | ⚠️ Not Explicit | ✅ Built | Button renamed to 'On My Radar' in home/page.tsx. Badge counter shows item count. Underlying data still called dailyBrief internally. MVP3 doc still says 'Daily Brief'. | MVP
Daily Brief email send (external morning digest) | Today / Home | Xan (21 Feb), Multiple | ✅ In Doc | ⚠️ Mock / Partial | API routes exist (/api/email/daily-brief, /api/cron/daily-brief). Loops integration wired. Needs production Loops API key and real data to be live. | MVP
What Needs Your Attention + Coming Up blocks | Today / Home | MVP3 Doc | ✅ In Doc | ✅ Built | Core Today page structure. Action items and commitments rendered with context drawer on selection. | MVP
Incomplete task carry-forward and ageing | Today / Home | Ken x G (15 Apr), UI changes doc | ⚠️ Not Explicit | ❌ Not Built | Discussed in meetings: cards should persist and show amber border at 1 day overdue, red at 2+ days. Not yet codified in code or MVP3 doc. | MVP
Tomo inline chat on Today / Home | Today / Home | MVP3 Doc | ✅ In Doc | ✅ Built | Inline chat embedded in home page, always visible. Context-aware suggestion chips. | MVP
Re-engagement urgent flag (LP emails after silence) | Today / Home | MVP3 Doc §11.8 | ✅ In Doc | ⚠️ Mock / Partial | Logic referenced in dailyBriefFromToday.ts and tomo-activity-feed.ts. Rule-based detection exists in mock data. Needs real signal computation from synced email. | MVP
Attachment prompt in commitment drawer | Today / Home | UI review (15 Apr), UI changes doc | ⚠️ Not Explicit | ✅ Built | AttachDocumentModal component built and wired into commitment drawer panel. User can choose file; filenames shown above CTAs per commitment id. | MVP
Two chip types: execution (silent) vs draft-producing | Today / Home | Ken x G (15 Apr), UI changes doc | ⚠️ Not Explicit | ✅ Built | drawer-section-2-tomo-chat.tsx has separate executionChips and draftChips sections with distinct test-ids and behaviour. | MVP
PIPELINE
Pipeline page with funnel view | Pipeline | PAG Painpoints, Multiple | ✅ In Doc | ✅ Built | Pipeline page exists with funnelRef, stage distribution, and list management. Natural language + structured filtering. | MVP
Named pipeline filters (Drifting, Quiet/Fat Middle, Re-engaged, One-Way) | Pipeline | MVP3 Doc §11.9 | ✅ In Doc | ⚠️ Mock / Partial | Relationship bands (Heating Up, Active-Stable, Cooling, Stalled) exist. Specific practitioner-named filters from §11.9 not confirmed in UI. | MVP
Natural language list building / filtering | Pipeline | Xan (21 Feb), TR Capital (13 Apr) | ✅ In Doc | ✅ Built | relationships-filter-chat.tsx and parseFilterPrompt.ts handle NL filtering. Pipeline Tomo chat chip: 'Who qualifies?' | MVP
Manual prospect entry (+ button / ad-hoc add) | Pipeline | Ken x G (15 Apr), Geoff/Ken (16 Apr) | ⚠️ Not Explicit | ✅ Built | NewContactModal component built and imported in relationships/page.tsx. relationships-provider.tsx notes 'manually added contacts (persisted)'. | MVP
Conference attendee list ingestion | Pipeline | Xan (21 Feb) | ❌ Excluded | ❌ Not Built | Upload PDF attendee list → prep outreach per person. Not in MVP3 or codebase. High value for roadshow prep use case. | Post-MVP Q3
Three-Touch Qualification Sequence | Pipeline | MVP3 Doc §11.10 | ✅ In Doc | ✅ Built | pb-three-touch-qualification playbook in mockPlaybooks.ts. Three-touch qualify for fat-middle/cold LPs: insight → direction question → qualifying close. GP approves every touch. | MVP
RELATIONSHIPS
Relationship signal flags (Green/Amber/Red) | Relationships | Xan (21 Feb), Edgar (2 Mar), Multiple | ✅ In Doc | ✅ Built | Bands: Heating Up, Active-Stable, Cooling, Stalled. Insights page tracks signal coverage %. Amber/red colour used in insights. Production computation needs real email sync. | MVP
Reply velocity and engagement signals | Relationships | MVP3 Doc §12.3 | ✅ In Doc | ⚠️ Mock / Partial | Signal schema defined in MVP3. Mock data reflects signal states. Real computation (reply latency rolling window) not yet wired to live email. | MVP
Meeting prep brief (first-class workflow outcome) | Relationships | Xan (21 Feb), TR Capital (13 Apr), MVP3 Doc §11.5 | ✅ In Doc | ⚠️ Mock / Partial | Meeting prep briefs referenced in mock data and Tomo assistance responses. Playbook step exists. Needs: signal line, overdue commitment flags, deep link to LP profile per UI review decisions. | MVP
Signal line in meeting brief (e.g. 'Frank's reply time shortened') | Relationships | UI changes doc (17 Apr) | ⚠️ Not Explicit | ❌ Not Built | Directional signal line in meeting prep brief not yet built. Discussed and decided in UI changes doc but not in MVP3 doc or code. | MVP
Overdue commitment flags in meeting brief | Relationships | UI changes doc (17 Apr) | ⚠️ Not Explicit | ❌ Not Built | Red flag + age for commitments past promised date not yet built in brief component. | MVP
Email deep link (open thread in Gmail / Outlook) | Relationships | UI review (15 Apr), UI changes doc | ⚠️ Not Explicit | ⚠️ Mock / Partial | LinkedIn URL deep link exists (data-testid='today-commitment-open-linkedin'). Gmail/Outlook thread deep link not confirmed in code. | MVP
Warm intro detection | Relationships | MVP3 Doc §11.14 | ✅ In Doc | ✅ Built | Warm Intro Tracker playbook with Detect & Log step. Workflow classifies intro emails, creates relationship record, prepares draft reply workflow. | MVP
Retroactive email/calendar ingestion (up to 90 days) | Relationships | Ken x Geoff (11 Apr), MVP3 Doc §11.1 | ✅ In Doc | ⚠️ Mock / Partial | Onboarding step references 90-day email history. Insights page notes 'baseline from calendar history at onboarding'. Real OAuth + ingestion pipeline not yet built. | MVP
Post-meeting capture (structured notes, <60 seconds) | Relationships | MVP3 Doc §7, §11.15 | ✅ In Doc | ✅ Built | Post-Meeting Execution playbook (pb-post-meeting) built with full workflow steps. Tomo surfaces it after meetings. Level A web-based capture in scope. | MVP
Deep personalisation from conversation details (pets, birthdays etc.) | Relationships | Xan (21 Feb) | ❌ Excluded | ❌ Not Built | Capturing and surfacing personal LP details in meeting prep. Not in MVP3 scope or codebase. | Post-MVP Q4
WORKFLOWS & PLAYBOOKS
Workflow automation with 4 playbooks | Workflows | TR Capital (13 Apr), Multiple | ✅ In Doc | ✅ Built | 4 playbooks built: Warm Intro Tracker, Post-Meeting Execution, Update → Follow-Up, DDQ Response Engine. Visual process flow, AI chat to edit steps. | MVP
DDQ Response Engine (auto-draft with human approval) | Workflows | Edgar (2 Mar), Ken x Geoff (11 Apr) | ⚠️ Not Explicit | ✅ Built | DDQ Response Engine is one of the 4 built playbooks. MVP3 doc lists 'richer drafting support' as post-MVP directionally, but it's already built as a playbook. | MVP
Follow-up draft generation (tone-dependent, <5 edits target) | Workflows | Edgar (2 Mar), TR Capital (13 Apr), MVP3 Doc §11.6 | ✅ In Doc | ✅ Built | Follow-up drafts generated in Tomo orchestrate API with tone parameter. Draft chips in drawer. Tone calibration referenced in settings. | MVP
Tone calibration (drafts match GP writing style) | Workflows | UI changes doc, MVP3 Doc §11.11 | ✅ In Doc | ⚠️ Mock / Partial | Tone parameter in orchestrate API (route.ts line 499). Insights page references 're-running tone calibration in Settings'. Settings UI for calibration not confirmed as fully built. | MVP
Workflow creator chat (natural language to create/edit workflows) | Workflows | Internal | ✅ In Doc | ✅ Built | workflow-creator-chat.tsx built. Uses /api/tomo/orchestrate with streaming. Real AI editing via update_workflow tool. | MVP
Trip / roadshow orchestration | Workflows | Edgar (2 Mar) | ❌ Excluded | ❌ Not Built | Batch emails and scheduling around a roadshow trip. Not in MVP3 or codebase. High value for active fundraisers. | Post-MVP Q3
Multi-party scheduling agent | Workflows | Xan (21 Feb) | ❌ Excluded | ❌ Not Built | Explicitly excluded in MVP3 §8. scheduling-find-time-modal.tsx exists for single-party time finding only. | Post-MVP Q4
TOMO AI
Agent orchestration (Tomo coordinates context, not just chatbot) | Tomo AI | MVP3 Doc §3.3 | ✅ In Doc | ✅ Built | /api/tomo/orchestrate endpoint with streaming. Handles: filter, workflow, crm, draft tools. Surface parameter (general/drawer/workflow) controls context. | MVP
Context-aware suggestion chips per page/entity | Tomo AI | MVP3 Doc | ✅ In Doc | ✅ Built | app-shell.tsx generates chips per section (pipeline, relationships, etc.). Drawer chips are context-locked to selected entity. | MVP
Real streaming AI (all surfaces) | Tomo AI | APP_SUMMARY_FOR_AI_REVIEW.md | ⚠️ Not Explicit | ⚠️ Mock / Partial | Real streaming only on Workflows page currently. Other pages use mock responses. Listed as key enhancement area in APP_SUMMARY. | MVP
Semantic search / RAG over emails and documents | Tomo AI | Ken x Geoff (11 Apr), Ken x G (15 Apr) | ❌ Excluded | ❌ Not Built | MVP3 §12.1 explicitly defers vector DB + RAG. MVP uses bounded SQL retrieval. Confirmed post-MVP by Ken and MVP3 doc. | Post-MVP Q3
INTEGRATIONS
Google Workspace / Microsoft 365 (email, calendar, contacts) | Integrations | MVP3 Doc §3.1 | ✅ In Doc | ⚠️ Mock / Partial | Onboarding has 8-step OAuth flow UI for Google + Microsoft. Stubbed OAuth in prototype. Real token exchange and ingestion pipeline not built. | MVP
CSV-first import and onboarding sequence | Integrations | TR Capital (13 Apr), MVP3 Doc §11.2 | ✅ In Doc | ✅ Built | Step 6 of onboarding: Contact import. relationshipsCsv.ts and RELATIONSHIPS_CSV_UPLOAD_INVESTIGATION.md confirm this is in scope and partially built. | MVP
Affinity CRM integration | Integrations | Xan (21 Feb), TR Capital (13 Apr), MVP3 Doc §3.2 | ✅ In Doc | ⚠️ Mock / Partial | Settings page has Affinity connect UI with list ID + API token fields. API endpoint structure planned. Not production-live. | MVP
Google Sheets export | Integrations | MVP3 Doc §3.2 | ✅ In Doc | ⚠️ Mock / Partial | Settings UI references Google Sheets (google_sheets_connected field). export/mock-relationships.csv exists. Full export pipeline not confirmed as live. | MVP
Slack integration (daily brief notifications) | Integrations | Ken x Geoff (11 Apr), MVP3 Doc §3.2 | ✅ In Doc | ⚠️ Mock / Partial | Settings has slackDigest toggle and slack_connected schema. Loops used for email delivery. Slack delivery channel not confirmed as live. | MVP
Broader Slack workflows (beyond daily brief) | Integrations | Ken x Geoff (11 Apr) | ❌ Excluded | ❌ Not Built | Explicitly excluded in MVP3 §8. Only scoped daily brief notification in MVP. | Post-MVP Q4
Telegram | Integrations | Multiple | ❌ Excluded | ❌ Not Built | Explicitly excluded in MVP3 §8. Icon exists in /public/icons/telegram.svg but no integration. | Post-MVP Q4
Backstop CRM integration | Integrations | TR Capital (13 Apr) | ❌ Excluded | ❌ Not Built | Explicitly excluded in MVP3 §8 ('Additional CRM integrations beyond Affinity and Google Sheets'). TR Capital uses Backstop — key blocker for that client. | Post-MVP Q3
LinkedIn integration (prospect import / research) | Integrations | Multiple | ❌ Excluded | ❌ Not Built | linkedInUrl field exists in data model and today-commitment-open-linkedin deep link. No import or API integration. Not in MVP3. | Post-MVP Q3
Meeting bot / transcript ingestion | Integrations | Multiple | ❌ Excluded | ❌ Not Built | Explicitly excluded in MVP3 §8. Post-meeting capture is web-based (no bot). Transcript ingestion is post-MVP expansion. | Post-MVP Q4
SETTINGS & INFRASTRUCTURE
Settings (Profile, Funds, Integrations, Notifications, Billing) | Settings | MVP3 Doc §2.9 | ✅ In Doc | ✅ Built | Settings page fully structured with all 5 sections. Billing links to Stripe Customer Portal. Fund manager built. | MVP
Auth + Onboarding (8-step setup) | Settings | MVP3 Doc | ✅ In Doc | ⚠️ Mock / Partial | UI fully built: auth (merged sign-in/up, OAuth buttons, plan selection) + 8-step onboarding. Backed by localStorage mock. Firebase Auth planned. | MVP
RBAC (Admin, Partner, Analyst roles for Team workspaces) | Settings | MVP3 Doc §4 | ✅ In Doc | ⚠️ Mock / Partial | Individual/Team plan selection in onboarding. RBAC schema commented in settings (SQL comments). Server-side enforcement not built. | MVP
Stripe billing (Individual + Team plans) | Settings | MVP3 Doc §5 | ✅ In Doc | ⚠️ Mock / Partial | Settings Billing section references Stripe Customer Portal. Stripe flows are placeholder in prototype. | MVP
Activity audit trail | Settings | MVP3 Doc §11.12 | ✅ In Doc | ✅ Built | /activity page with fund/type/date filters. tomo-activity-feed.ts generates activity items including system and user actions. | MVP
Real backend (Supabase + Firebase Auth) | Settings | APP_SUMMARY §7 | ✅ In Doc | ❌ Not Built | Currently all localStorage. Supabase + Firebase Auth planned but not built. Key prerequisite for production. | MVP
ANALYTICS / REPORTING
Insights / Analytics page (Execution Health, Pipeline Intelligence, Raise Momentum) | Analytics | Internal / Code | ⚠️ Not Explicit | ✅ Built | /insights page built with 4 sections: Execution Health, Pipeline Intelligence, Raise Momentum, Capital Influenced. Not in MVP3 nav — this is beyond the spec. | MVP
LP Network page | Analytics | Internal / Code | ⚠️ Not Explicit | ✅ Built | /lp-network page with qualified LP cards and introduction status. Not in MVP3 nav — extra feature built above spec. | MVP
KPI / funnel visualisation (time in stage, conversion) | Analytics | PAG Painpoints | ⚠️ Not Explicit | ⚠️ Mock / Partial | Insights page has stage progression rate (available after 30 days) and pipeline intelligence section. Full funnel time-in-stage KPIs not confirmed. | Post-MVP Q3
Management reports | Analytics | PAG Painpoints | ❌ Excluded | ❌ Not Built | Formatted management reports (PDF, scheduled) not in MVP3 or codebase. | Post-MVP Q3
Data aggregation across external systems | Analytics | PAG Painpoints | ❌ Excluded | ❌ Not Built | Pulling and aggregating data from fund admin, CRM, email, and other systems in one view. Not in MVP3 scope. | Post-MVP Q4
POST-MVP (FUTURE ROADMAP)
Fund data auto-extraction (eliminate Excel/copy-paste) | Post-MVP | Edgar (2 Mar) | ❌ Excluded | ❌ Not Built | Auto-pull performance data from fund admin (State Street etc.) into fact sheets. Removes manual Excel → CRM step. High pain point for Edgar-type users. | Post-MVP Q3
Conference attendee ingestion + outreach prep | Post-MVP | Xan (21 Feb) | ❌ Excluded | ❌ Not Built | Upload PDF attendee list for a conference → Tomo preps personalised outreach emails per person. | Post-MVP Q3
Trip / roadshow orchestration | Post-MVP | Edgar (2 Mar) | ❌ Excluded | ❌ Not Built | Batch scheduling and emails around a roadshow trip. Geo-aware scheduling across timezone clusters. | Post-MVP Q3
Backstop CRM integration | Post-MVP | TR Capital (13 Apr) | ❌ Excluded | ❌ Not Built | Required to unlock TR Capital as a client. Backstop API access needs investigation. | Post-MVP Q3
LinkedIn integration (prospect import + research) | Post-MVP | Multiple | ❌ Excluded | ❌ Not Built | Import prospects from LinkedIn, surface connection paths, prep outreach. URL field in data model already exists. | Post-MVP Q3
Semantic search / RAG over email + document corpus | Post-MVP | Edgar (2 Mar), Ken x Geoff (11 Apr) | ❌ Excluded | ❌ Not Built | Vector DB + semantic recall over full email history and document repository. Enables open-ended LP research queries. | Post-MVP Q3
Deep personalisation (surface personal LP details in briefs) | Post-MVP | Xan (21 Feb) | ❌ Excluded | ❌ Not Built | Capture personal details from conversations (pets, family, interests) and surface before next LP interaction. | Post-MVP Q4
Meeting bot + transcript ingestion | Post-MVP | Multiple | ❌ Excluded | ❌ Not Built | Tomo bot joins meetings, generates transcript, feeds into post-meeting workflow automatically. | Post-MVP Q4
Broader Slack / Telegram workflows | Post-MVP | Multiple | ❌ Excluded | ❌ Not Built | Full Slack-native operating model beyond daily brief. Telegram delivery channel. | Post-MVP Q4
Multi-party scheduling agent | Post-MVP | Xan (21 Feb) | ❌ Excluded | ❌ Not Built | Fully autonomous multi-party calendar coordination. Single-party find-time modal exists. | Post-MVP Q4
Cmd+K global omnibar search | Post-MVP | Internal | ❌ Excluded | ❌ Not Built | Global fast search across all entities. Header search in MVP; Cmd+K omnibar is post-MVP per §8. | Post-MVP Q4
Management reports (formatted PDF, scheduled) | Post-MVP | PAG Painpoints | ❌ Excluded | ❌ Not Built | Scheduled management-quality reports sent to stakeholders. | Post-MVP Q4

## Legend
Legend
CODE STATUS
✅ Built | Feature is confirmed in the codebase (production or mock)
⚠️ Mock / Partial | UI built but backed by mock data or stub API; needs real integration
❌ Not Built | Not yet in codebase
MVP3 DOC STATUS
✅ In Doc | Explicitly specified in Tomo_MVP_3_amended_v5.docx
⚠️ Not Explicit | Built or decided in meetings but not written into MVP3 doc yet
❌ Excluded | Explicitly marked out-of-scope or post-MVP in the doc
ROADMAP TIER
MVP | Target for current MVP3 release
Post-MVP Q3 | Next priority after MVP launch
Post-MVP Q4 | Longer-term enhancement
TBD | Timing to be decided
ROW COLOURS
Green row | Feature confirmed as built in code
Amber row | Feature partially built / mock only
Red row | Feature needed for MVP but not yet built
Purple row | Post-MVP feature — not expected in this release